## Sheet1
DRAFT ASCP 5-Year Strategic Plan Worksheet
| Purple = in progress | Green = Completed | Blue = On Hold
This DRAFT 5-Year Strategic Plan Worksheet was created in 2018 (and updated with progress in 2019) to serve as an internal guide for ASCP staff to help the organization prioritize efforts. Please note that this is a DRAFT. We have not yet converted this into a formal written report, but we wanted to make this plan available to the campus community in the interest of transparency and more productive engagement with students. If you are considering submitting a proposal for ASCP funding, please spend a few minutes reviewing this strategic plan to see how your idea aligns and to make your propsal stronger. These
Alternative Transportation: Increase the percentage of campus commuters using only forms of alternative transportation including biking, train, bus, scootering, or walking by 5% before 2021
Goal #1: | Increase Bike Ridership by 25% by 2021: We currently average 496 riders on good-weather days. Goal: Average 620 per day
Impact: | A 25% increase in bike ridership during the 80 good-weather days would avoid an additional 90.93 MTCO2e/year
Objectives | Strategy/Action | Who is Responsible? | When should this be accomplished? | Purpose of Action | How will effectiveness be measured? | Update
1.1 | Build out a North/South Bike Lane | Chris Herr | Before August 1st, 2020 | To reduce the chances of bikers receiving tickets in dismount zones and help move bikers away from pedestrian walkways | Continued and more frequent bike counts will give us feedback on whether or not ridership has increase. Also, the Alternative Transporation Survey will give additional feedback. | Beginning proposal process
1.2 | Add at least 60 covered and secured bike parking locations | Chris Herr | End of FY 2020 | To reduce bike theft on campus, one of the biggest reasons constituents don't bike | Continued and more frequent bike counts will give us feedback on whether or not ridership has increase. Also, the Alternative Transporation Survey will give additional feedback. | Project breaking ground August 1st, 2020
1.3 | Increase number of bike counts throughout the year | Chris Herr | Begin new counts in Fall, 2019 | To gather more detailed information regarding bike commuter numbers and location usages | This information will be used to help us determine our bike ridership more accurately and detect any changes due to our efforts
1.4 | Re-evaluate our bike rack distribution | Chris Herr | Before end of FY 2020 | To address concerns that there are not enough bike racks on campus despite our less than 50% occupancy rates | Continued and more frequent bike counts will give us feedback on whether or not ridership has increased. Also, the Alternative Transporation Survey will give additional feedback.
1.5 | Develop and distrubute alternative transportation survey | Chris Herr/Jackson | Before end of FY 2019 | To determine what obstacles remain regarding biking to campus and gain other insights that can help us encourage biking | This tool will be used to evaluate the effectiveness of our Alternative Transportation programming and projects. | Available on ASCP website
1.6 | Host two Bike to Work Day Events per Year | Chris Herr | On-going | To incentivize regular and new commuters. This will help get new commuters to try biking to campus | We will track the number of participants and regularly administer a survey | Cancelled due to COVID-19
Goal #2: | Encourage Alternative Transportation (other than bikes)
Impact: | Reducing Single Occupancy Vehicle Commutes and Increasing Public or Alternative Transportation which will ultimately reduce emissions
Objectives | Strategy/Action | Who is Responsible? | When should this be accomplished? | Purpose of Action | How will effectiveness be measured?
2.1 | Add Special Racks at Bike Parking Locations Specifically for Mopeds, Scooters, Skateboards, etc. | Chris Herr | End of FY 2019 | To Provide a safe storage option for these non-traditional modes of transport | The use of these spots will be monitered during the bike counts | Special racks incorporated in bike shelters
2.2 | Collaborate with SGAs and SACAB to host RTD resources during Welcome Week and other relevant dates |  | On-going | To connect students to transit and route planning resources to overcome barriers | Future transportation surveys will be compared to baseline in 2018/19
2.3 | Transit to Work Day |  | Spring 2020 |  |  | Cancelled due to COVID-19
Education and Outreach: Increase campus awareness of ASCP and general sustainability concepts by 25%
Goal #1: | Students, faculty and staff will be aware of the ASCP and sustainability events and programming on campus. They will have a basic understanding of key sustainability concepts and how their actions can make an impact.
Objectives | Strategy/Action | Who is Responsible? | When should this be accomplished? | Purpose of Action | How will effectiveness be measured?
1.1 | Develop a survey assessment that will help determine the Auraria Campus population's understanding of important concepts | Jackie Slocombe/MPA Capstone Student | Complete the Survey by December 31st, 2018 | Once we have a baseline, we can continue to survey our population to see if we detect any changes | 1. Definition of 'important concepts' is developed 2. A baseline is established before the beginning of the 2019/2020 school year 3. A percentage increase goal is set once baseline data is collected. 75% of survey respondents report awareness of ASCP. A percentage increase goal of 20% increase in understanding of general sustainability concepts from 2019 baseline. | 607 responses
1.2 | Revive newsletter: bi-weekly or monthly publications including ASCP events, feature articles, ASCP updates. | Jackie Slocombe | Publish first newsletter late September. Then monthly or bi-weekly thereafter. | Keep campus community in the loop with ASCP, provide opportunities to engage, generate buzz about ASCP. | Tracking metrics in Constant Contact and inbound "leads" for partnering with ASCP (student, club or dept.). Click throughs, open rate, etc.
1.3 | Increased tabling presence | Outreach and Ed Coord/Whole team | Fall 2018: tabling at all relevant events. Spring 2019: revamp setup. | Increase likelihood of engagement and increase knowledge of ASCP | Number of events tabled, surveys received.
1.4 | Integration into the Admissions/Visitation process and marketing materials | Outreach and Education Coordinator | Spring 2021 | Attract students interested in sustiainability to campus and improve reputation as a "green" school. Could be presentation, self-guided tour, or print material
1.5 | Increase brand recognition across campus | All | Fall 2018 - ongoing | Distribution of swag and conversion of all old logo to new logo | All old logos replaced with new across campus and observation of students with swag
1.6 | SGA and SACAB listening tour each fall |  | On-going | Increase awareness of resources for students pursuing sustainability efforts
1.7 | Coalesce ASCPAC and Eco Rep program |  | Fall 2019 | Leverage the student voice to reach the three institutions
1.8 | Re-evaluate proposal submission process |  | Spring 2020 | Increase student participation and success |  | Define Grant Proposal structure and implement
Goal #2: | ENGAGE: Increase student engagement with sustainability initatives on campus.
Objectives | Strategy/Action | Who is Responsible? | When should this be accomplished? | Purpose of Action | How will effectiveness be measured?
2.1 | Develop "Sustainability Heroes" Program | ASCP Team | Quarterly or monthly | Generate intercampus competition and pride around sustainability interventions. Celebrate. Create campus cohesion. Incentivize action. | # of groups submitting bids, increased participation in programming
2.2 | Host one educational/behavior change event per month | Outreach and Ed Coordinator | Monthly. Generate list of events by mid-September 2018 | Increase ASCP visibility. Increase awareness of environmental issues. Through partnership, reach populations we wouldn't otherwise reach. | 1 event/month target, learning outcomes achieved and reasonable increase in student participants
2.3 | Develop and implement green ambassador/volunteer program (green events, Green Offices auditing, waste audit, waste diversion at events) | Outreach and Ed Coordinator/Green Offices Manager | Spring, 2019 | Provide ongoing volunteer opportunities so we have an answer to the question: "how can I get involved?" | # of volunteers engaged, increased awareness of ASCP and increase in overall understanding of sustainability concepts
2.5 | Green Offices Program | Karmen/Jackie | Pilot early fall 2018. Launch end of 2018 or early 2019. | Engage staff and faculty and encourage behavior change across campus | MTCO2 avoided by interventions: lightbulbs and power strips replaced, compost bins deployed.
2.6 | Did You Know Campaign | ASCP Team | Fall 2018 | Increase awareness of sustainability issues and encourage behavior change. | # of users reached (social media), # of behavior change actions reported (app or online "game" interface), increase in overall understanding of sustainability concepts
Goal #3: | EXPAND/COLLABORATE: ASCP will be integrated into departments across campus and collaborate to achieve shared goals and to further our mission
Objectives | Strategy/Action | Who is Responsible? | When should this be accomplished? | Purpose of Action | How will effectiveness be measured?
3.1 | Develop a strong working relationship with facilities, custodial, and grounds | Chris and Outreach and Ed | Immediately | We rely heavily on facilities and grounds crew and need to have them on our team. | Strength of relationships with facilities and grounds leading to more effective project management and program outcomes
3.2 | Develop Staff/Faculty coalition to engage all stakeholders in broader conversation and connect the dots |  | Spring 2019 | Engage stakeholders, connect the dots | Impact of coalition initiatives and projects, increased faculty/staff awareness of ASCP
3.3 | Integrate sustainability training into employee orientation and ongoing trainings in a meaningful and effective way | Outreach and Ed | Spring 2020 | Increase staff awareness and participation. Create "role models" for students | Presence of enhanced sustainability training in employee orientation.
3.4 | Develop guidelines for sustainable event planning for distribution to all event planning staff across campus | Chris Herr | Complete by Fall, 2019 and distribute prior to spring semester | To encourage more sustainable event planning practices | Increased waste diversion, staff and faculty 'buy-in' to ASCP sustainability goals
Goal #4: | Educate: Create opportunities for our program an dinterested students to participate in understanding sustainability within the context of social justice
Objectives | Strategy/Action | Who is Responsible? | When should this be accomplished? | Purpose of Action | How will effectiveness be measured?
4.1 | Service Days on campus | Jackie | Fall 2019 | Engage students with the community
4.2 | Community service days - Local Ag, Food Bank, Trail Maintenance, Conservation efforts | Jackie/Chris | Fall 2019 | Engage students with the community
4.3 | Workshops focused on the disproportionate effects of climate change on low-income populations | Jackie | Fall 2019 | Educate students on the social impacts of climate change
Energy Efficiency:
Goal #1: | Reduce Campus Electricity Consumption by 10% by 2023 (below 2018 baseline: 49,285,653 kWh)
Impact:
Objectives | Strategy/Action | Who is Responsible? | When should this be accomplished? | Purpose of Action | How will effectiveness be measured?
1.1 | Increase the quantity and scope of Energy Efficiency projects or retrofits | Chris Herr | On-going | To identify opportunities for high-impact Energy Efficiency projects | N/A
1.2 | Hire an additional staff member (Sustainability Coordinator) that will allow the Sustainability Officer to focus on Energy Management projects and monitoring | Chris Herr | End of FY 2018 | To allow additional time dedicated to energy management and data collection, greater capacity for research regarding impactful practices and projects | N/A
1.3 | Petition for the establishment of an Energy Manager position that would be housed separately within AHEC and optimize energy expenditures, reducing our usage | Chris Herr | TBD | To closely monitor energy use and identify ways in which it can be reduced or otherwise optimized. It will save AHEC on utility costs | N/A
1.4 | Develop a comprehensive greenhouse gas inventory for the purpose of establishing baseline data that will inform future progress and goals | Chris/Jackie | Summer 2019 | More clearly define our progress regarding our climate action goals and to help identify our largest inefficiencies | N/A | Available on the ASCP website
1.5 | Investigate and research the feasibility of installing a better metering and/or monitoring system to improve data quality |  |  | Improve our baseline and increase liklihood of identifying inefficiencies
Goal #2: | Implement Behavioral Change Programs
Impact: | These efforts will average an annual savings of 5% from our overall energy use after 2023 which will account for a savings of 1807 MTCO2e/year
Objectives | Strategy/Action | Who is Responsible? | When should this be accomplished? | Purpose of Action | How will effectiveness be measured?
2.1 | Green Offices Program (see Education and Outreach) | Karmen (Jackie backup) | Pilot early fall 2018. Launch end of 2018 or early 2019. | Engage staff and faculty and encourage behavior change across campus | MTCO2 avoided by interventions: lightbulbs and power strips replaced, compost bins deployed.
2.2 | Did you Know Campaign (see Education and Outreach) | Laura/Jackie | Spring 2019 | Engage students through education and actionable steps each person can take | (see Education and Outreach)
Food/Garden and Landscaping
Goal #1: | Elevate presence of garden on campus and leverage garden as a physical gathering space to bring people together around sustainability.
Objectives | Strategy/Action | Who is Responsible? | When should this be accomplished? | Purpose of Action | How will effectiveness be measured?
1.1 | Host at least one event per month in garden during season | Hire part-time garden manager (student) | Each month. Proposed events due April 1 each year | Elevate presence of garden on campus and leverage garden as a physical gathering space to bring people together around sustainability. Generate SCP publicity | Event turnout? Demand for more events? Survey feedback?
1.2 | Collaborate with Homelessness Initiative to host a Harvest Dinner/Festival or Indigenous Peoples Dinner | Garden Manager/Sustainability Coordinator | Fall 2020 | Increase awareness of local food seasonality/highlight social justice issues surrounding sustainability | Event turnout and learning outcomes achieved
Goal #2: | Increase education and awareness around sustainable agricultural practices and the impact of the industrial food system and offer more access to locally procured food
Objectives | Strategy/Action | Who is Responsible? | When should this be accomplished? | Purpose of Action | How will effectiveness be measured?
2.1 | Increase volume and scope of gardening workshops | Future Garden Manager | 2019 growing season | Increase education on food production/growing techniques (via workshops) | Attendees reached/# events held, increased understanding
2.2 | Host one educational event per year focusing on industrialized food systems | Chris/Jackie | Once each school year | Educate students about the impact of their food choices | Attendees reached/# events held, increased understanding | Factory Harming Event in fall of 2020
2.3 | Pursue a farmer's market on campus | Chris/Jackie | 2021 | Increase access to healthy, local, organic food | Increase access and education around local food | Proposed via Dr. Jackson's class
2.4 | Educate campus community about leveraging WIC and SNAP benefits for local and organic food access | Sustainability Coordinator | 2021 | Decrease vehicle miles traveled, oppose pesticide use | Increase access and education around local food
2.5 | Increase partnerships with food and agriculture related groups on campus | Sustainability Coordinator | Spring 2019 | Exploit available resources, gain larger audience via partnering with health resources, urban agriculture programs, and culinary programs | Increase access and education around local food
Goal #3: | Increase local food procurement among campus vendors where possible
Objectives | Strategy/Action | Who is Responsible? | When should this be accomplished? | Purpose of Action | How will effectiveness be measured?
2.1 | Conduct inventory/assessment of campus vendors and ability to increase responsible food procurement. Work with Real Food Challenge and Farm to School to offer strategies for increased local food procurement | Cassy | 2020 | Increase local food procurement among vendors | N/A
2.2 | Evaluate policies for opportunities to encourage local business and affordable/healthier options for students on campus | Chris Herr/SACAB | 2022 | Increase local food procurement among vendors | Policy or guiding document adopted for each institution
Goal #4: | Increase sustainble landcaping practices on campus
Objective | Strategy/Action | Who is Responsible? | When should this be accomplished? | Purpose of Action | How will effectiveness be measured?
4.1 | Develop a policy that would eliminate turf as an option on 8-foot wide strips | Chris Herr | Fall 2020 | Reduce toxic chemicals in water runoff | Water use reduced | In progress, now in the form of the Landscape Use Guidelines
4.2 | Encourage transition to more organic and natural pest control and fertilizer | Chris Herr | 2019 | Reduce toxic chemicals in water runoff and protect pollinators | Adoption of steam-based weed killer and dramatic reduction in glysophate use | Steam Weed Killer purchased in fall 2019
4.3 | Support Auraria's cooperation with Denver's Green Building Ordinance | Chris Herr | 2022 | Provide guiding language that would encourage compliance | Adoption of policy or guiding document for each institution
Renewable Energy
Goal #1: | 2.5MWs of campus energy from renewable sources by Dec 2025
Impact | 8092.6 MTCO2e saved and substaincial fiscal return for the ASCP and Campus
Objectives | Strategy/Action | Who is Responsible? | When should this be accomplished? | Purpose of Action | How will effectiveness be measured?
1.1 | 1 MW solar by 2020; 2.5 MW by 2025 | Jackie/Chris | 2020 and 2025 | Decrease campus reliance on fossil fuels/support clean grid | MW procured | After new array, currently at 824 kW
1.2 | Complete a Solar Master Plan | Jackie/Chris/Karmen | Fall 2018 | Determine feasibility and action plan to pursue solar on campus. Implement policies around roof replacement. | Report Complete
1.3 | Explore other options for renewable procurement (wind, geothermal, biofuels) and update goals annually to reflect opportunity | Chris/Jackie | bi-annually | Decrease campus reliance on fossil fuels/support clean grid | N/A
1.4 | Support Auraria's cooperation with Denver's Green Building Ordinance to encourage more solar energy on campus | Chris Herr | Spring 2019 | Provide guiding language that would encourage compliance | Adoption of policy or guiding document for each institution, as outlined in the PV Roadmap
Goal #2: | Increase awareness of campus renewable energy efforts
Impact | Incerease student demand and support for solar and energy efficiency projects
Objectives | Strategy/Action | Who is Responsible? | When should this be accomplished? | Purpose of Action | How will effectiveness be measured?
2.1 | Clear, durable signs in arts and future buildings (and parking lots) showcasing solar efforts | Evan | Directly after install (2019) | Increase awareness of Auraria's solar generation | 25% of survey respondents (see outreach and ed) report knowledge of arts solar
2.2 | Install highly visible, small-scale solar on campus for educational purposes | Chris | 2023 | Increase student excitement and awareness about renewable energy on campus | The annual survey will be ammended to include this project and gauge student awareness
2.3 | Integrate projects into student research and applicable departments | Jackie
Staffing/Operating
Goal #1: | Increase ASCP Capacity
Impact: | The ability to properly maintain the mission and vision of the ASCP while pushing forward to increase impact
Objectives | Strategy/Action | Who is Responsible? | When should this be accomplished? | Purpose of Action | How will effectiveness be measured?
1.1 | Hire a Sustainability Coordinator | Chris Herr | Before January, 2019 | To expand the ASCP capacity and begin improving the program | All metrics will be achieved
1.2 | Lobby for the development of an Energy Manger position | Chris Herr | ASAP | To hire someone dedicated to tracking energy use and optimizing/reducing expenditures in the area | N/A
1.3 | Develop a Staff and Faculty optional Payroll Deduction program | Chris Herr |  | To diversify our funding and engage the 7,000 constituents on campus that do not currently contribute to the program but may like to | The funds would be kept separate from the student fee funds and tracked to determine interest
Waste Diversion
Goal #1: | Increase our Waste Diversion Rate to 35% before end of FY 2022 (Currently 18.28%)
Impact:
Objectives | Strategy/Action | Who is Responsible? | When should this be accomplished? | Purpose of Action | How will effectiveness be measured?
1.1 | Event Compost Expansion | Chris Herr | Spring 2019 | To offer compost services to resource-intensive events so that compost can be recovered without establishing complex systems campus-wide | By monitoring the pounds of compost recovered and applying this to our Waste Diversion Rate | Launched
1.2 | Compost Expansion | Chris Herr | End of FY 2020 | To offer compost services campus-wide | By monitoring the pounds of compost recovered and applying this to our Waste Diversion Rate
1.3 | Plastic Reduction Plan | Chris Herr | End of FY 2020 | To encourage vendors and caterers to reduce or eliminate plastic use | Observing change, establishing policy | SACAB currently in pursuit
1.4 | Improve Waste Bin Signage | Chris Herr | Spring 2020 | To eliminate confusion and implement a standard display for trash, recycling and compost campus-wide | By monitoring the pounds of compost recovered and applying this to our Waste Diversion Rate | Almost ready
1.5 | Add dumpsters for easier implementation |  | End of FY 2019
1.6 | Compost Fee Referednum | Chris Herr | Spring 2020 |  |  | Approved by student body 70% - 30% in Spring 2020
1.7 | Hire Zero Waste Specialist | Chris Herr | Summer 2020 |  |  | Approved
1.8 | Waste education via waste audits, bin-side education, Zero Waste Sorting Guide | Cassy | On-going | increase student engagement and awareness
Water Conservation
Goal #1: | Reduce Campus Water Use by 10% before 2022 (below 2017 baseline of 70 million gals/year)
Objectives | Strategy/Action | Who is Responsible? | When should this be accomplished? | Purpose of Action | How will effectiveness be measured?
1.1 | Retrofits | Chris Herr | ASAP | Determine where retrofits are still possible and determine plan for executing | On a per-unit replaced basis | Not necessary
1.2 | Irrigation Audit | Chris Herr | By 2020 | We need to take a look at how the rain sensors are working, what the water usage looks like |  | Facilities currently conducting
1.3 | Develop Water Action Plan in partnership with OWOW | Chris/Jackie | 2020 |  |  | Available on the ASCP website
1.4 | Indoor Water Fixture Audit |  | 2019 | Identify indoor replacement opportunities |  | Completed in Fall 2019
Goal #2: | Behavior Change Initiatives
Objectives | Strategy/Action | Who is Responsible? | When should this be accomplished? | Purpose of Action | How will effectiveness be measured?
2.1 | "gamify" positive behavioral changes via digital tracking of impact | Chris/Cupanion? | ASAP | Provide students the ability to track how much water they save with each refill via an app |  | In talks with Pips

## Sheet2
Goal #1: | Increase Bike Ridership by 35% by 2021: We currently average 496 riders on good-weather days. Goal: Average 620 per day
Impact: | A 25% increase in bike ridership during the 80 good-weather days would avoid an additional 90.93 MTCO2e/year
1.3 | Increase number of bike counts throughout the year | Chris Herr | Begin new counts in Fall, 2018 | To gather more detailed information regarding bike commuter numbers and location usages | This information will be used to help us determine our bike ridership more accurately and detect any changes due to our efforts
1.4 | Re-evaluate our bike rack distribution | Chris Herr | Before end of FY 2019 | To address concerns that there are not enough bike racks on campus despite out less than 50% occupancy rates | Continued and more frequent bike counts will give us feedback on whether or not ridership has increase. Also, the Alternative Transporation Survey will give additional feedback.
1.6 | Host two Bike to Work Day Events per Year | Chris Herr | On-going | To incentivize regular and new commuters. This will help get new commuters to try biking to campus | We will track the number of participants and regularly administer a survey